## Safety checks
Play Area. Routine Inspection Checklist
2026-05-05
Instructions for completion:
1. Use a copy of this check sheet to record each inspection.
2. Tick the check box if no faults are found. Mark a cross if faults are found.
3. Add details of any faults, including action taken if any.
4. Use the following master pages for reference to guide you.
5. Retain this completed check sheet for a minimum of 21 years.
Asset | Check (✔ or ✘ ) | Faults | Comments
Signage | ✔
Gates | ✘ | Still functioning well but treatment needs finishing
Litter Bins | ✔ |  | Small bin has been relocated near Highgate Lane entrance
Seating | ✘ | Still more benches need attention | Green bench still needs a base
Swing – Junior 1 Bay 2 Seat | ✔
Multiplay – Slide Climber |  | New lamiinated platform still needs fitting
Swing – Mixed – 2 Bay 1 | ✔ | Some bird prevention strips need replacing
Group 2 Toddler | ✔ | Some bird prevemtion strips need replacing
Football Goals | ✔ | Some of the concrete is beginning to show at the base of one of the goal posts | Pitch could do with some attention as difficult to play on at the moment. Nets to be installed. New bolts needed to secure struts to hold nets.
Perimeter fencing | ✘ | Loose fencing at entrance to park at Highgate Lane end | Really needs extending slightly and new fence posts installed. Also new gate to be purchased through funding.
Metal shelter | ✔
Name of Inpector | Date | Signature
John Moulson | 2026-04-29 | JP Moulson
General Comments | Need to keep an eye on molehills at the football pitch end of the park. Suggest we get Ian back to sort them before it gets worse.